## Appendix B Update - 31DEC2020
Service ID | Pre-Transition Satellite | Pre-Transition Transponder | Pre-Transition Center Frequency (MHz) | Pre-Transition Bandwidth (MHz) | Post-Transition Satellite | Post-Transition Transponder | Post-Transition Center Frequency (MHz) | Post-Transition Bandwidth (MHz) | Transition Start (yyyy-mm-dd) | Transition End (yyyy-mm-dd) | Technology Upgrade / Type | Transition Status | Actual Transition End (yyy-mm-dd) | Note
AMC-11/11R_06C_3820_36 | AMC-11/11R | 06C | 3820 | 36 | AMC-11/11R | 10C | 3900 | 36 | 2021-01-01 | 2021-01-01 | N | C | 2020-10-01
AMC-11/11R_08C_3860_36 | AMC-11/11R | 08C | 3860 | 36 | AMC-11/11R | 04C | 3780 | 36 | 2020-12-01 | 2020-12-19 | N | A,C | 2020-12-19 | Non-CONUS service move needed to clear transponder for CONUS service
AMC-11/11R_12C_3940_36 | AMC-11/11R | 12C | 3940 | 36 | AMC-11/11R | 24C | 4180 | 36 | 2023-04-01 | 2023-05-31 | N | P
AMC-11/11R_14C_3980_36 | AMC-11/11R | 14C | 3980 | 36 | AMC-10R | 20C | 4100 | 36 | 2023-01-01 | 2023-01-01 | N | P
AMC-11/11R_24C_4180_36 | AMC-11/11R | 24C | 4180 | 36 | AMC-10R | 17C | 4049 | 18 | 2023-01-01 | 2023-03-31 | N | P
AMC-3_03C_3760_36 | AMC-3 | 03C | 3760 | 36 | [5 empty] | x | Refer to Appendix B | P
AMC-3_04C_3780_36 | AMC-3 | 04C | 3780 | 36 | [5 empty] | x | Refer to Appendix B | P
AMC-3_05C_3800_36 | AMC-3 | 05C | 3800 | 36 | [5 empty] | x | Refer to Appendix B | P
AMC-3_06C_3820_36 | AMC-3 | 06C | 3820 | 36 | [5 empty] | x | Refer to Appendix B | P
AMC-3_10C_3900_36 | AMC-3 | 10C | 3900 | 36 | [5 empty] | x | Refer to Appendix B | P
AMC-3_15C_4000_36 | AMC-3 | 15C | 4000 | 36 | [5 empty] | x | Refer to Appendix B | P
NSS-10_EAH14/NAH14_3980_36 | NSS-10 | EAH14/NAH14 | 3980 | 36 | NSS-10 | EAH14/NAH14 | 3980 | 36 | 2020-06-01 | 2023-05-31 | G | P
NSS-10_EAH20/NAH20_4100_36 | NSS-10 | EAH20/NAH20 | 4100 | 36 | NSS-10 | EAH20/NAH20 | 4100 | 36 | 2020-06-01 | 2022-05-31 | G | A |  | Necessary to clear antenna for TT&C for new/replacement satellites
NSS-10_EAH22/NAH22_4125.6_7.2 | NSS-10 | EAH22/NAH22 | 4125.6 | 7.2 | NSS-10 | EAH22/NAH22 | 4125.6 | 7.2 | 2020-06-01 | 2022-05-31 | G | A |  | Necessary to clear antenna for TT&C for new/replacement satellites
NSS-10_EAH24/NAH24_4189_36 | NSS-10 | EAH24/NAH24 | 4189 | 36 | NSS-10 | EAH24/NAH24 | 4189 | 36 | 2020-06-01 | 2022-05-31 | G | A |  | Necessary to clear antenna for TT&C for new/replacement satellites
NSS-10_EAV15/NAV15_4000_36 | NSS-10 | EAV15/NAV15 | 4000 | 36 | NSS-10 | EAV15/NAV15 | 4000 | 36 | 2020-06-01 | 2023-05-31 | G | P
NSS-10_EAV17/NAV17_4040_36 | NSS-10 | EAV17/NAV17 | 4040 | 36 | NSS-10 | EAV17/NAV17 | 4040 | 36 | 2020-06-01 | 2022-05-31 | G | A |  | Necessary to clear antenna for TT&C for new/replacement satellites
NSS-10_NAV02/NAH02_3740_36 | NSS-10 | NAV02/NAH02 | 3740 | 36 | NSS-10 | NAV02/NAH02 | 3740 | 36 | 2020-06-01 | 2023-05-31 | G | P
NSS-10_NAV06/NAH06_3820_36 | NSS-10 | NAV06/NAH06 | 3820 | 36 | NSS-10 | NAV06/NAH06 | 3820 | 36 | 2020-06-01 | 2023-05-31 | G | P
NSS-10_NAV08/NAH08_3860_36 | NSS-10 | NAV08/NAH08 | 3860 | 36 | NSS-10 | NAV08/NAH08 | 3860 | 36 | 2020-06-01 | 2023-05-31 | G | P
NSS-10_NAV10/NAH10_3900_36 | NSS-10 | NAV10/NAH10 | 3900 | 36 | NSS-10 | NAV10/NAH10 | 3900 | 36 | 2020-06-01 | 2023-05-31 | G | P
NSS-10_SAV21/NAV21_4120_36 | NSS-10 | SAV21/NAV21 | 4120 | 36 | NSS-10 | SAV21/NAV21 | 4120 | 36 | 2020-06-01 | 2022-05-31 | G | A |  | Necessary to clear antenna for TT&C for new/replacement satellites
NSS-9_EHL03/EHR03_3834_48 | NSS-9 | EHL03/EHR03 | 3834 | 48 | NSS-9 | EHL03/EHR03 | 3834 | 48 | 2020-06-01 | 2021-08-31 | G | P
NSS-9_EHL04/EHR04_3885_2.2 | NSS-9 | EHL04/EHR04 | 3885 | 2.2 | NSS-9 | EHL04/EHR04 | 3885 | 2.2 | 2020-06-01 | 2023-05-31 | G | P
NSS-9_EHL04/EHR04_3923.25_0.3 | NSS-9 | EHL04/EHR04 | 3923.25 | 0.3 | SES-14 | HEL-03/HER-03 | 3740.45 | 2.5 | 2020-06-01 | 2021-06-30 | N | C | 2020-10-12
NSS-9_EHL04/EHR04_3924.55_2.3 | NSS-9 | EHL04/EHR04 | 3924.55 | 2.3 | NSS-9 | GLL10/GLR10 | 4194.35 | 2.3 | 2020-06-01 | 2021-06-30 | N | C | 2020-10-12
NSS-9_EHR03/EHL03_3822_72 | NSS-9 | EHR03/EHL03 | 3822 | 72 | NSS-9 | EHR03/EHL03 | 3822 | 72 | 2020-06-01 | 2021-08-31 | G | P
NSS-9_GLL05/GLR05_3967_3.8 | NSS-9 | GLL05/GLR05 | 3967 | 3.8 | NSS-9 | GLL05/GLR05 | 3967 | 3.8 | 2020-06-01 | 2023-05-31 | G | P
NSS-9_GLL05/GLR05_3970.75_3.7 | NSS-9 | GLL05/GLR05 | 3970.75 | 3.7 | NSS-9 | GLL05/GLR05 | 3970.75 | 3.7 | 2020-06-01 | 2023-05-31 | G | P
SES-1_01C_3706_8 | SES-1 | 01C | 3706 | 8 | SES-1 | 12C | 3930 | 8 | 2021-01-01 | 2021-03-31 | N | P
SES-1_01C_3716_6 | SES-1 | 01C | 3716 | 6 | SES-1 | 15C | 4010.8 | 6 | 2020-06-01 | 2020-12-31 | N | C | 2020-10-07
SES-1_01C_3725_12 | SES-1 | 01C | 3725 | 12 | SES-1 | 12C | 3952 | 12 | 2021-01-01 | 2021-03-31 | N | P
SES-1_01C_3733_4 | SES-1 | 01C | 3733 | 4 | SES-1 | 12C | 3924 | 4 | 2021-01-01 | 2021-03-31 | N | P
SES-1_01C_3736.1_1 | SES-1 | 01C | 3736.1 | 1 | SES-1 | 15C | 4015.5 | 1 | 2020-06-01 | 2020-12-31 | N | C | 2020-09-08
SES-1_01C_3737.8_0.4 | SES-1 | 01C | 3737.8 | 0.4 | SES-1 | 15C | 4014.5 | 0.4 | 2020-06-01 | 2020-12-31 | N | C | 2020-09-29
SES-1_03C_3744_4 | SES-1 | 03C | 3744 | 4 | SES-1 | 12C | 3936 | 4 | 2021-01-01 | 2021-03-31 | N | P
SES-1_03C_3748_4 | SES-1 | 03C | 3748 | 4 | SES-1 | 12C | 3940 | 4 | 2021-01-01 | 2021-03-31 | N | P
SES-1_03C_3750.9_1.4-1 | SES-1 | 03C | 3750.9 | 1.4 | SES-1 | 13C | 4162.5 | 1.4 | 2020-06-01 | 2021-05-31 | N | C | 2020-08-28
SES-1_03C_3750.9_1.4-2 | SES-1 | 13C | 4162.5 | 1.4 | SES-11 | 23C | 4162.5 | 1.4 | 2023-01-01 | 2023-05-31 | N | D |  | Replaced with single 7.2 MHz entry: SES-1_13C_3954.525_7.2
SES-1_03C_3752.5_1.8-1 | SES-1 | 03C | 3752.5 | 1.8 | SES-1 | 13C | 4164.1 | 1.8 | 2020-06-01 | 2021-05-31 | N | C | 2020-08-28
SES-1_03C_3752.5_1.8-2 | SES-1 | 13C | 4164.1 | 1.8 | SES-11 | 23C | 4164.1 | 1.8 | 2023-01-01 | 2023-05-31 | N | D |  | Replaced with single 7.2 MHz entry: SES-1_13C_3954.525_7.2
SES-1_03C_3756.9_2 | SES-1 | 03C | 3756.9 | 2 | SES-1 | 15C | 4017 | 2 | 2020-06-01 | 2020-12-31 | N | C | 2020-09-08
SES-1_03C_3758.2_0.2-1 | SES-1 | 03C | 3758.2 | 0.2 | SES-1 | 13C | 4165.3 | 0.2 | 2020-06-01 | 2021-05-31 | N | C | 2020-08-28
SES-1_03C_3758.2_0.2-2 | SES-1 | 13C | 4165.3 | 0.2 | SES-11 | 23C | 4165.3 | 0.2 | 2023-01-01 | 2023-05-31 | N | D |  | Replaced with single 7.2 MHz entry: SES-1_13C_3954.525_7.2
SES-1_03C_3758_0.2-1 | SES-1 | 03C | 3758 | 0.2 | SES-1 | 13C | 4165.1 | 0.2 | 2020-06-01 | 2021-05-31 | N | C | 2020-08-28
SES-1_03C_3758_0.2-2 | SES-1 | 13C | 4165.1 | 0.2 | SES-11 | 23C | 4165.1 | 0.2 | 2023-01-01 | 2023-05-31 | N | D |  | Replaced with single 7.2 MHz entry: SES-1_13C_3954.525_7.2
SES-1_03C_3761.8_1.8-1 | SES-1 | 03C | 3761.8 | 1.8 | SES-1 | 13C | 4166.3 | 1.8 | 2020-06-01 | 2021-05-31 | N | C | 2020-08-28
SES-1_03C_3761.8_1.8-2 | SES-1 | 13C | 4166.3 | 1.8 | SES-11 | 23C | 4166.3 | 1.8 | 2023-01-01 | 2023-05-31 | N | D |  | Replaced with single 7.2 MHz entry: SES-1_13C_3954.525_7.2
SES-1_03C_3764.7_4 | SES-1 | 03C | 3764.7 | 4 | SES-1 | 12C | 3944 | 4 | 2021-01-01 | 2021-03-31 | N | P
SES-1_03C_3768.3_1.8-1 | SES-1 | 03C | 3768.3 | 1.8 | SES-1 | 13C | 4168.1 | 1.8 | 2020-06-01 | 2021-05-31 | N | C | 2020-08-28
SES-1_03C_3768.3_1.8-2 | SES-1 | 13C | 4168.1 | 1.8 | SES-11 | 23C | 4168.1 | 1.8 | 2023-01-01 | 2023-05-31 | N | D |  | Replaced with single 7.2 MHz entry: SES-1_13C_3954.525_7.2
SES-1_03C_3769.5_0.3 | SES-1 | 03C | 3769.5 | 0.3 | SES-1 | 15C | 4014.85 | 0.3 | 2020-06-01 | 2020-12-31 | N | C | 2020-09-09
SES-1_03C_3772.7_6 | SES-1 | 03C | 3772.7 | 6 | SES-1 | 15C | 4004.8 | 6 | 2021-01-01 | 2021-03-31 | N | P
SES-1_07C_3840_36 | SES-1 | 07C | 3840 | 36 | SES-1 | 18C | 4060 | 36 | 2023-04-01 | 2023-05-31 | N | P
SES-1_09C_3880_36 | SES-1 | 09C | 3880 | 36 | SES-1 | 23C | 4160 | 36 | 2023-01-01 | 2023-05-31 | N | P
SES-1_10C_3900_36 | SES-1 | 10C | 3900 | 36 | AMC-10R | 22C | 4140 | 36 | 2023-01-01 | 2023-03-31 | N | P
SES-1_11C_3920_36 | SES-1 | 11C | 3920 | 36 | SES-1 | 21C | 4120 | 36 | 2022-01-01 | 2022-06-30 | N | P
SES-1_13C_3947.225_2 | SES-1 | 13C | 3947.225 | 2 | SES-11 | 23C | 4158.6 | 2 | 2023-01-01 | 2023-05-31 | N | P
SES-1_13C_3949.225_2 | SES-1 | 13C | 3949.225 | 2 | SES-11 | 23C | 4160.6 | 2 | 2023-01-01 | 2023-05-31 | N | P
SES-1_13C_3950.325_0.2 | SES-1 | 13C | 3950.325 | 0.2 | SES-11 | 23C | 4161.7 | 0.2 | 2023-01-01 | 2023-05-31 | N | P
SES-1_13C_3950.55_0.25 | SES-1 | 13C | 3950.55 | 0.25 | SES-1 | 15C | 4013.925 | 0.25 | 2020-06-01 | 2020-12-31 | N | C | 2020-11-03
SES-1_13C_3950.8_0.25 | SES-1 | 13C | 3950.8 | 0.25 | SES-1 | 15C | 4014.175 | 0.25 | 2020-06-01 | 2020-12-31 | N | C | 2020-11-03
SES-1_13C_3954.525_7.2 | SES-1 | 13C | 3954.525 | 7.2 | SES-11 | 23C | 4145.6 | 7.2 | 2023-01-01 | 2023-05-31 | N | A |  | Consolidation of SES-1_03C_3750.9_1.4-2, SES-1_03C_3752.5_1.8-2, SES-1_03C_3758.2_0.2-2, SES-1_03C_3758_0.2-2, SES-1_03C_3761.8_1.8-2, SES-1_03C_3768.3_1.8-2
SES-1_14C_3980_36 | SES-1 | 14C | 3980 | 36 | SES-1 | 16C | 4020 | 36 | 2022-01-01 | 2022-05-31 | N | P
SES-1_18C_4060_36 | SES-1 | 18C | 4060 | 36 | AMC-10R | 24C | 4180 | 36 | 2023-01-01 | 2023-03-31 | N | P
SES-1_24C_4180_36-1 | SES-1 | 24C | 4180 | 36 | SES-1 | 08C | 3860 | 36 | 2021-01-01 | 2021-05-31 | N | P
SES-1_24C_4180_36-2 | SES-1 | 08C | 3860 | 36 | AMC-10R | 19C | 4080 | 36 | 2023-01-01 | 2023-05-31 | N | P
SES-11_01C_3706_8 | SES-11 | 01C | 3706 | 8 | SES-11 | 23C | 4173.5 | 9 | 2020-11-01 | 2021-02-28 | N | I
SES-11_01C_3714.175_0.75 | SES-11 | 01C | 3714.175 | 0.75 | SES-11 | 23C | 4152.525 | 0.75 | 2020-11-01 | 2021-02-28 | N | P
SES-11_01C_3720.8_5.5 | SES-11 | 01C | 3720.8 | 5.5 | SES-11 | 23C | 4144.75 | 5.5 | 2020-11-01 | 2021-02-28 | N | I
SES-11_01C_3737.425_0.4 | SES-11 | 01C | 3737.425 | 0.4 | SES-11 | 23C | 4151.75 | 0.4 | 2020-11-01 | 2021-02-28 | N | C | 2020-11-16
SES-11_02C_3740_36 | SES-11 | 02C | 3740 | 36 | AMC-11/11R | 09C | 3880 | 36 | 2021-01-01 | 2021-05-31 | C/M | P
SES-11_04C_3780_36 | SES-11 | 04C | 3780 | 36 | SES-11 | 22C | 4140 | 36 | 2020-12-01 | 2021-05-31 | N | I
SES-11_05C_3800_36 | SES-11 | 05C | 3800 | 36 | AMC-11/11R | 11C | 3920 | 36 | 2021-01-01 | 2021-05-31 | C/M | P
SES-11_06C_3820_36 | SES-11 | 06C | 3820 | 36 | AMC-11/11R | 13C | 3960 | 36 | 2021-01-01 | 2021-05-31 | C/M | P
SES-11_07C_3840_36 | SES-11 | 07C | 3840 | 36 | AMC-11/11R | 17C | 4040 | 36 | 2021-01-01 | 2022-05-31 | C/M | P
SES-11_08C_3860_36 | SES-11 | 08C | 3860 | 36 | AMC-11/11R | 18C | 4060 | 36 | 2021-01-01 | 2022-05-31 | C/M | P
SES-11_09C_3880_36 | SES-11 | 09C | 3880 | 36 | AMC-11/11R | 15C | 4000 | 36 | 2021-12-01 | 2022-05-31 | C/M | P
SES-11_10C_3900_36 | SES-11 | 10C | 3900 | 36 | SES-11 | 16C | 4020 | 36 | 2022-06-01 | 2022-11-30 | N | P
SES-11_11C_3920_36 | SES-11 | 11C | 3920 | 36 | SES-11 | 19C | 4080 | 36 | 2022-06-01 | 2022-10-31 | N | P
SES-11_12C_3940_36 | SES-11 | 12C | 3940 | 36 | SES-11 | 18C | 4060 | 36 | 2023-04-01 | 2023-05-31 | N | P
SES-11_13C_3960_36 | SES-11 | 13C | 3960 | 36 | AMC-11/11R | 21C | 4120 | 36 | 2021-01-01 | 2022-05-31 | C/M | P
SES-11_14C_3980_36 | SES-11 | 14C | 3980 | 36 | AMC-11/11R | 16C | 4020 | 36 | 2021-12-01 | 2022-05-31 | C/M | P
SES-11_15C_4000_36 | SES-11 | 15C | 4000 | 36 | AMC-11/11R | 21C | 4120 | 36 | 2021-01-01 | 2022-05-31 | C/M | P
SES-11_16C_4020_36 | SES-11 | 16C | 4020 | 36 | AMC-11/11R | 22C | 4140 | 36 | 2021-01-01 | 2022-05-31 | C/M | P
SES-11_18C_4060_36 | SES-11 | 18C | 4060 | 36 | AMC-10R | 21C | 4120 | 36 | 2023-01-01 | 2023-03-31 | N | P
SES-11_19C_4080_36 | SES-11 | 19C | 4080 | 36 | AMC-11/11R | 15C | 4009 | 18 | 2021-01-01 | 2022-05-31 | C/M | P
SES-11_23C_4160_36 | SES-11 | 23C | 4160 | 36 | SES-11 | 13C | 3960 | 36 | 2020-06-01 | 2020-10-31 | N | C | 2020-11-03
SES-14_GLR16/GLL16_4047_4 | SES-14 | GLR16/GLL16 | 4047 | 4 | SES-14 | GLR16/GLL16 | 4047 | 4 | 2020-06-01 | 2022-05-31 | G | A |  | Necessary to clear antenna for TT&C for new/replacement satellites
SES-14_GLR16/GLL16_4065.1724_6 | SES-14 | GLR16/GLL16 | 4065.1724 | 6 | SES-14 | GLR16/GLL16 | 4065.1724 | 6 | 2020-06-01 | 2022-05-31 | G | A |  | Necessary to clear antenna for TT&C for new/replacement satellites
SES-14_GLR16/GLL16_4072.5_1 | SES-14 | GLR16/GLL16 | 4072.5 | 1 | SES-14 | GLR16/GLL16 | 4072.5 | 1 | 2020-06-01 | 2022-05-31 | G | A |  | Necessary to clear antenna for TT&C for new/replacement satellites
SES-14_HEL-03/HER-03_3717.7_21.4 | SES-14 | HEL-03/HER-03 | 3717.7 | 21.4 | SES-14 | HEL-03/HER-03 | 3717.7 | 21.4 | 2020-06-01 | 2021-08-31 | G | P
SES-14_HEL-03/HER-03_3733.3_9.8 | SES-14 | HEL-03/HER-03 | 3733.3 | 9.8 | SES-14 | HEL-03/HER-03 | 3733.3 | 9.8 | 2020-06-01 | 2021-08-31 | G | P
SES-14_HEL-03/HER-03_3761_36 | SES-14 | HEL-03/HER-03 | 3761 | 36 | SES-14 | HEL-03/HER-03 | 3761 | 36 | 2020-06-01 | 2021-08-31 | G | D |  | Service no longer transitioning
SES-14_HEL09/HER09_3883_36 | SES-14 | HEL09/HER09 | 3883 | 36 | SES-14 | HEL09/HER09 | 3883 | 36 | 2020-06-01 | 2022-05-31 | G | A |  | Necessary to clear antenna for TT&C for new/replacement satellites
SES-14_HEL-11/HER-11_3908.9_7.8 | SES-14 | HEL-11/HER-11 | 3908.9 | 7.8 | SES-14 | HEL-11/HER-11 | 3908.9 | 7.8 | 2020-06-01 | 2023-05-31 | G | P
SES-14_HEL-11/HER-11_3937.7_3.6 | SES-14 | HEL-11/HER-11 | 3937.7 | 3.6 | SES-14 | HEL-11/HER-11 | 3937.7 | 3.6 | 2020-06-01 | 2023-05-31 | G | P
SES-14_HEL-11/HER-11_3940.25_1.5 | SES-14 | HEL-11/HER-11 | 3940.25 | 1.5 | SES-14 | HEL-11/HER-11 | 3940.25 | 1.5 | 2020-06-01 | 2023-05-31 | G | D |  | Service no longer transitioning
SES-14_HEL19/HER19_4156_79 | SES-14 | HEL19/HER19 | 4156 | 79 | SES-14 | HEL19/HER19 | 4156 | 79 | 2020-06-01 | 2022-05-31 | G | A |  | Necessary to clear antenna for TT&C for new/replacement satellites
SES-14_HER-04/HEL-04_3743_72 | SES-14 | HER-04/HEL-04 | 3743 | 72 | SES-14 | HER-04/HEL-04 | 3743 | 72 | 2020-06-01 | 2021-08-31 | G | D |  | Service no longer transitioning
SES-14_HER-08/HEL-08_3851_8 | SES-14 | HER-08/HEL-08 | 3851 | 8 | SES-14 | HER-08/HEL-08 | 3851 | 8 | 2020-06-01 | 2023-05-31 | G | P
SES-14_HER-08/HEL-08_3854.15_13.7 | SES-14 | HER-08/HEL-08 | 3854.15 | 13.7 | SES-14 | HER-08/HEL-08 | 3854.15 | 13.7 | 2020-06-01 | 2023-05-31 | G | P
SES-14_HER-08/HEL-08_3858_6 | SES-14 | HER-08/HEL-08 | 3858 | 6 | SES-14 | HER-08/HEL-08 | 3858 | 6 | 2020-06-01 | 2023-05-31 | G | D |  | Service no longer transitioning
SES-14_HER-12/HEL-12_3923_36 | SES-14 | HER-12/HEL-12 | 3923 | 36 | SES-14 | HER-12/HEL-12 | 3923 | 36 | 2020-06-01 | 2023-05-31 | G | D |  | Service no longer transitioning
SES-14_HER-14/HEL-14_3995_72 | SES-14 | HER-14/HEL-14 | 3995 | 72 | SES-14 | HER-14/HEL-14 | 3995 | 72 | 2020-06-01 | 2023-05-31 | G | P
SES-14_HER18/HEL18_4095_36 | SES-14 | HER18/HEL18 | 4095 | 36 | SES-14 | HER18/HEL18 | 4095 | 36 | 2020-06-01 | 2022-05-31 | G | A |  | Necessary to clear antenna for TT&C for new/replacement satellites
SES-14_HER-20/HEL-20_4160.65_15.3 | SES-14 | HER-20/HEL-20 | 4160.65 | 15.3 | SES-14 | HER-20/HEL-20 | 4160.65 | 15.3 | 2020-06-01 | 2023-05-31 | G | P
SES-2_01C_3720_36 | SES-2 | 01C | 3720 | 36 | SES-2 | 19C | 4080 | 36 | 2020-09-06 | 2020-09-26 | N | C | 2020-10-06
SES-2_07C_3828.7145_0.6 | SES-2 | 07C | 3828.7145 | 0.6 | SES-2 | 23C | 4164.8 | 0.6 | 2020-06-01 | 2020-08-31 | N | C | 2020-08-14
SES-2_07C_3832.45_6.5 | SES-2 | 07C | 3832.45 | 6.5 | SES-2 | 23C | 4176 | 4 | 2020-06-03 | 2020-09-02 | N | C | 2020-08-31
SES-2_07C_3851.5131_9.7 | SES-2 | 07C | 3851.5131 | 9.7 | SES-2 | 23C | 4146.85 | 9.7 | 2020-06-01 | 2020-08-31 | N | C, A | 2020-07-28 | Service erroneously omitted from 28 Ocober Transition Plan filing
SES-2_07C_3857.2_0.2 | SES-2 | 07C | 3857.2 | 0.2 | SES-2 | 23C | 4165.2 | 0.2 | 2020-06-01 | 2020-08-31 | N | C | 2020-08-31
SES-2_07C_3857.55_0.5 | SES-2 | 07C | 3857.55 | 0.5 | SES-2 | 23C | 4165.55 | 0.5 | 2020-06-01 | 2020-08-31 | N | C | 2020-08-31
SES-2_07C_3857.9_0.2 | SES-2 | 07C | 3857.9 | 0.2 | SES-2 | 23C | 4165.9 | 0.2 | 2020-06-01 | 2020-08-31 | N | C | 2020-08-31
SES-2_08C_3860_36 | SES-2 | 08C | 3860 | 36 | SES-2 | 18C | 4060 | 36 | 2020-12-01 | 2020-12-31 | N | C | 2020-12-15
SES-2_09C_3863_8 | SES-2 | 09C | 3863 | 8 | SES-2 | 23C | 4170 | 8 | 2020-06-01 | 2020-06-01 | N | C, A | 2020-06-01 | Service erroneously omitted from 28 Ocober Transition Plan filing
SES-2_10C_3886.5_9 | SES-2 | 10C | 3886.5 | 9 | SES-2 | 20C | 4086.5 | 9 | 2020-11-01 | 2020-11-21 | N | D |  | Service no longer transitioning
SES-2_10C_3904.5_27 | SES-2 | 10C | 3904.5 | 27 | SES-2 | 20C | 4104.5 | 27 | 2020-11-01 | 2020-12-31 | N | P
SES-2_12C_3935.4_12.4 | SES-2 | 12C | 3935.4 | 12.4 | SES-2 | 22C | 4151 | 12.4 | 2020-10-02 | 2020-10-24 | N | C | 2020-10-23
SES-2_12C_3957.1035_0.8 | SES-2 | 12C | 3957.1035 | 0.8 | SES-2 | 22C | 4157.6 | 0.8 | 2020-10-02 | 2020-10-24 | N | C | 2020-10-26
SES-2_13C_3957.525_0.5 | SES-2 | 13C | 3957.525 | 0.5 | SES-2 | 21C | 4127.325 | 0.5 | 2020-10-30 | 2021-05-31 | N | P
SES-2_13C_3960.675_5.8 | SES-2 | 13C | 3960.675 | 5.8 | SES-2 | 21C | 4120.675 | 5.8 | 2020-10-30 | 2021-05-31 | N | P
SES-2_13C_3964.475_1.8 | SES-2 | 13C | 3964.475 | 1.8 | SES-2 | 21C | 4124.475 | 1.8 | 2020-10-30 | 2021-05-31 | N | P
SES-2_13C_3965.625_0.5 | SES-2 | 13C | 3965.625 | 0.5 | SES-2 | 21C | 4125.625 | 0.5 | 2020-10-30 | 2021-05-31 | N | P
SES-2_13C_3966.0425_0.335 | SES-2 | 13C | 3966.0425 | 0.335 | SES-2 | 21C | 4129.7525 | 0.335 | 2020-10-30 | 2021-05-31 | N | P
SES-2_13C_3966.81_1.2 | SES-2 | 13C | 3966.81 | 1.2 | SES-2 | 21C | 4126.475 | 1.2 | 2020-10-30 | 2021-05-31 | N | P
SES-2_13C_3968.4_0.35 | SES-2 | 13C | 3968.4 | 0.35 | SES-2 | 23C | 4164.325 | 0.35 | 2020-07-08 | 2020-12-31 | N | P
SES-2_13C_3968.8_0.3 | SES-2 | 13C | 3968.8 | 0.3 | SES-2 | 21C | 4163.65 | 0.3 | 2020-10-30 | 2021-05-31 | N | C | 2020-10-05
SES-2_13C_3969.975_2.05 | SES-2 | 13C | 3969.975 | 2.05 | SES-2 | 21C | 4116.75 | 2.05 | 2020-10-30 | 2021-05-31 | N | P
SES-2_13C_3974.5_7 | SES-2 | 13C | 3974.5 | 7 | SES-2 | 21C | 4134.5 | 7 | 2020-10-30 | 2021-05-31 | N | P
SES-2_17C_4040_36 | SES-2 | 17C | 4040 | 36 | SES-2 | 13C | 3960 | 36 | 2021-06-01 | 2021-06-05 | N | P
SES-2_18C_4060_36 | SES-2 | 18C | 4060 | 36 | SES-2 | 10C | 3900 | 36 | 2020-11-22 | 2020-12-31 | N | P
SES-2_19C_4080_36 | SES-2 | 19C | 4080 | 36 | SES-2 | 07C | 3840 | 36 | 2020-09-04 | 2020-09-05 | N | C | 2020-09-17
SES-2_20C_4100_36 | SES-2 | 20C | 4100 | 36 | SES-2 | 12C | 3940 | 36 | 2020-10-25 | 2020-10-31 | N | C | 2020-11-18
SES-2_21C_4120_36 | SES-2 | 21C | 4120 | 36 | SES-2 | 01C | 3720 | 36 | 2020-10-13 | 2020-10-24 | N | C | 2020-11-12
SES-2_23C_4170_36 | SES-2 | 23C | 4170 | 36 | SES-2 | 09C | 3880 | 36 | 2020-05-22 | 2020-05-25 | N | C, A | 2020-05-25 | Service erroneously omitted from 28 Ocober Transition Plan filing
SES-3/3R_01C_3720_36 | SES-3/3R | 01C | 3720 | 36 | SES-3/3R | 19C | 4080 | 36 | 2020-12-01 | 2021-05-31 | N | P
SES-3/3R_03C_3760_36 | SES-3/3R | 03C | 3760 | 36 | SES-3/3R | 20C | 4100 | 36 | 2021-01-01 | 2021-05-31 | N | P
SES-3/3R_04C_3780_36 | SES-3/3R | 04C | 3780 | 36 | SES-3/3R | 09C | 3880 | 36 | 2021-05-01 | 2021-05-31 | N | P
SES-3/3R_08C_3860_36 | SES-3/3R | 08C | 3860 | 36 | AMC-10R | 18C | 4060 | 36 | 2023-01-01 | 2023-05-31 | N | P
SES-3/3R_10C_3900_36-1 | SES-3/3R | 10C | 3900 | 36 | AMC-10R | 16C | 4020 | 36 | 2023-01-01 | 2023-05-31 | N | P
SES-3/3R_10C_3900_36-2 | SES-3/3R | 10C | 3900 | 36 | SES-3/3R | 18C | 4060 | 36 | 2021-07-01 | 2021-12-31 | N | P
SES-3/3R_11C_3924.15_3.7 | SES-3/3R | 11C | 3924.15 | 3.7 | AMC-10R | 15C | 4005.85 | 3.7 | 2023-01-01 | 2023-05-31 | N | P
SES-3/3R_11C_3928.15_4.3 | SES-3/3R | 11C | 3928.15 | 4.3 | AMC-10R | 15C | 4009.85 | 4.3 | 2023-01-01 | 2023-05-31 | N | D |  | Service no longer transitioning
SES-3/3R_11C_3934.75_6.5 | SES-3/3R | 11C | 3934.75 | 6.5 | SES-11 | 17C | 4054.75 | 6.5 | 2020-06-01 | 2020-12-31 | N | I
SES-3/3R_12C_3925_6 | SES-3/3R | 12C | 3925 | 6 | AMC-10R | 15C | 4015 | 6 | 2023-01-01 | 2023-05-31 | N | P
SES-3/3R_12C_3943_30 | SES-3/3R | 12C | 3943 | 30 | AMC-10R | 16C | 4017 | 30 | 2023-01-01 | 2023-05-31 | N | P
SES-3/3R_13C_3960_36 | SES-3/3R | 13C | 3960 | 36 | AMC-10R | 22C | 4140 | 36 | 2023-01-01 | 2023-05-31 | N | P
SES-3/3R_14C_3972_20 | SES-3/3R | 14C | 3972 | 20 | SES-3/3R | 15C | 4009 | 18 | 2022-11-01 | 2023-05-31 | N | P
SES-3/3R_14C_3984.65_4 | SES-3/3R | 14C | 3984.65 | 4 | SES-11 | 23C | 4149.5 | 4 | 2023-01-01 | 2023-05-31 | N | P
SES-3/3R_14C_3990_6.7 | SES-3/3R | 14C | 3990 | 6.7 | AMC-10R | 16C | 4020 | 36 | 2023-01-01 | 2023-05-31 | N | P
SES-3/3R_14C_3996.8_2.4 | SES-3/3R | 14C | 3996.8 | 2.4 | SES-11 | 23C | 4154.1 | 2.4 | 2020-11-01 | 2021-02-28 | N | P
SES-3/3R_15C_4000_36 | SES-3/3R | 15C | 4000 | 36 | SES-3/3R | 22C | 4140 | 36 | 2022-04-01 | 2022-10-31 | N | P
SES-3/3R_22C_4140_36-1 | SES-3/3R | 22C | 4140 | 36 | SES-3/3R | 10C | 3900 | 36 | 2022-01-01 | 2022-03-31 | N | P
SES-3/3R_22C_4140_36-2 | SES-3/3R | 22C | 4140 | 36 | AMC-10R | 17C | 4031 | 18 | 2023-01-01 | 2023-03-31 | N | P
SES-4_EHL06/WHR06_3975.8_23.6 | SES-4 | EHL06/WHR06 | 3975.8 | 23.6 | SES-4 | EHL06/WHR06 | 4003.95 | 8.5 | 2020-06-01 | 2023-05-31 | N | C, A | 2020-06-19 | Service erroneously omitted from 28 Ocober Transition Plan filing
SES-4_EHL06/WHR06_4009.8_3.2 | SES-4 | EHL06/WHR06 | 4009.8 | 3.2 | SES-4 | EHL06/WHR06 | 3965.6 | 3.2 | 2020-06-01 | 2023-05-31 | N | C | 2020-09-02
SES-4_EHR03/WHL03_3796.8_4 | SES-4 | EHR03/WHL03 | 3796.8 | 4 | SES-4 | EHR03/WHL03 | 3796.8 | 4 | 2020-06-01 | 2021-11-30 | G | D |  | Service no longer transitioning
SES-4_EHR03/WHL03_3802.97_3.1 | SES-4 | EHR03/WHL03 | 3802.97 | 3.1 | SES-4 | EHR03/WHL03 | 3802.97 | 3.1 | 2020-06-01 | 2021-08-31 | G | P
SES-4_EHR03/WHL03_3809.42_1 | SES-4 | EHR03/WHL03 | 3809.42 | 1 | SES-4 | EHR03/WHL03 | 3809.42 | 1 | 2020-06-01 | 2021-08-31 | G | P
SES-4_EHR03/WHL03_3812.47_0.1 | SES-4 | EHR03/WHL03 | 3812.47 | 0.1 | SES-4 | EHR03/WHL03 | 3812.47 | 0.1 | 2020-06-01 | 2021-05-31 | N | C, A | 2020-07-10 | Service erroneously omitted from 28 Ocober Transition Plan filing
SES-4_EHR03/WHL03_3814.17_2.5 | SES-4 | EHR03/WHL03 | 3814.17 | 2.5 | SES-4 | EHR03/WHL03 | 3814.17 | 2.5 | 2020-06-01 | 2021-08-31 | G | P
SES-4_EHR03/WHL03_3816.67_2.5 | SES-4 | EHR03/WHL03 | 3816.67 | 2.5 | SES-4 | EHR03/WHL03 | 3816.67 | 2.5 | 2020-06-01 | 2021-08-31 | G | D |  | Service no longer transitioning
SES-4_EHR03/WHL03_3837.1_1.8 | SES-4 | EHR03/WHL03 | 3837.1 | 1.8 | SES-4 | GLR10/GLL10 | 4130.9 | 1.8 | 2020-06-01 | 2023-05-31 | N | P
SES-4_EUV03/WHR04_3888.75_18.5 | SES-4 | EUV03/WHR04 | 3888.75 | 18.5 | SES-4 | EUV03/WHR04 | 3888.75 | 18.5 | 2020-06-01 | 2023-05-31 | G | P
SES-4_EUV04/WHR05_3908.15_8.3 | SES-4 | EUV04/WHR05 | 3908.15 | 8.3 | SES-4 | EUV04/WHR05 | 3908.15 | 8.3 | 2020-06-01 | 2023-05-31 | G | P
SES-4_EUV04/WHR05_3915_5.4 | SES-4 | EUV04/WHR05 | 3915 | 5.4 | SES-4 | EUV04/WHR05 | 3915 | 5.4 | 2020-06-01 | 2023-05-31 | G | P
SES-4_EUV04/WHR05_3921.15_6.9 | SES-4 | EUV04/WHR05 | 3921.15 | 6.9 | SES-4 | EUV04/WHR05 | 3921.15 | 6.9 | 2020-06-01 | 2023-05-31 | G | P
SES-4_EUV04/WHR05_3932_8.2 | SES-4 | EUV04/WHR05 | 3932 | 8.2 | SES-4 | EUV04/WHR05 | 3932 | 8.2 | 2020-06-01 | 2023-05-31 | G | P
SES-4_EUV04/WHR05_3941.8_10.2 | SES-4 | EUV04/WHR04 | 3941.8 | 10.2 | SES-4 | WHR02/WHL02 | 3759.2096 | 2.9808 | 2020-06-01 | 2021-11-30 | G | D |  | Service no longer transitioning
SES-4_EUV04/WHR05_3955.45_5.1 | SES-4 | EUV04/WHR05 | 3955.45 | 5.1 | SES-4 | WHR02/WHL02 | 3770.9017 | 2.7651 | 2020-06-01 | 2021-11-30 | G | D |  | Service no longer transitioning
SES-4_GLL09/GLR09_4086.15_8.3 | SES-4 | GLL09/GLR09 | 4086.15 | 8.6 | SES-4 | GLL09/GLR09 | 4086.15 | 8.6 | 2020-06-01 | 2022-05-31 | G | A |  | Necessary to clear antenna for TT&C for new/replacement satellites
SES-4_GLL10/GLR10_4142.075_0.95 | SES-4 | GLL10/GLR10 | 4142.075 | 0.95 | SES-4 | GLL10/GLR10 | 4142.075 | 0.95 | 2020-06-01 | 2022-05-31 | G | A |  | Necessary to clear antenna for TT&C for new/replacement satellites
SES-4_GLL10/GLR10_4151.3_3 | SES-4 | GLL10/GLR10 | 4151.3 | 3 | SES-4 | GLL10/GLR10 | 4151.3 | 3 | 2020-06-01 | 2022-05-31 | G | A |  | Necessary to clear antenna for TT&C for new/replacement satellites
SES-4_GLL11/GLR11_4193.5002_9 | SES-4 | GLL11/GLR11 | 4193.5002 | 9 | SES-4 | GLL11/GLR11 | 4193.5002 | 9 | 2020-06-01 | 2022-05-31 | G | A |  | Necessary to clear antenna for TT&C for new/replacement satellites
SES-4_GLR09/GLL09_4111.7_12.6 | SES-4 | GLR09/GLL09 | 4111.7 | 12.6 | SES-4 | GLR09/GLL09 | 4111.7 | 12.6 | 2020-06-01 | 2022-05-31 | G | A |  | Necessary to clear antenna for TT&C for new/replacement satellites
SES-4_GLR10/GLL10_4153.3002_9.4 | SES-4 | GLR10/GLL10 | 4153.3002 | 9.4 | SES-4 | GLR10/GLL10 | 4153.3002 | 9.4 | 2020-06-01 | 2022-05-31 | G | A |  | Necessary to clear antenna for TT&C for new/replacement satellites
SES-4_GLR11/GLL11_4172.75_21.5 | SES-4 | GLR11/GLL11 | 4172.75 | 21.5 | SES-4 | GLR11/GLL11 | 4172.75 | 21.5 | 2020-06-01 | 2023-05-31 | G | D |  | Service no longer transitioning
SES-4_WHL02/WHR02_3772.0005_1.99 | SES-4 | WHL02/WHR02 | 3772.0005 | 1.99 | SES-4 | WHL02/WHR02 | 3772.0005 | 1.99 | 2020-06-01 | 2021-08-31 | G | A |  | Service erroneously omitted from 28 Ocober Transition Plan filing
SES-4_WHL03/WHR03_3810.15_7.7 | SES-4 | WHL03/WHR03 | 3810.15 | 7.7 | SES-4 | WHL07/WHR07 | 4027.898 | 7.7 | 2020-06-01 | 2021-05-31 | G | C, A, P | 2020-07-28 | Service has two transitions; change in frequency in Phase 1 and transition to the Hawley TT&C/Gateway in Phase 2
SES-4_WHL07/WHR07_4053.05_6.5 | SES-4 | WHL04/EUH03 | 4053.05 | 6.5 | SES-4 | WHLO4/EUH03 | 4053.05 | 6.5 | 2020-06-01 | 2022-05-31 | G | A |  | Necessary to clear antenna for TT&C for new/replacement satellites
SES-4_WHLO4/EUH03_3886.4_23 | SES-4 | WHL04/EUH03 | 3886.4 | 26 | SES-4 | WHLO4/EUH03 | 3886.4 | 26 | 2020-06-01 | 2022-05-31 | G | A |  | Necessary to clear antenna for TT&C for new/replacement satellites
SES-4_WHR02/WHL02_3728.5_47 | SES-4 | WHR02/WHL02 | 3728.5 | 47 | SES-4 | WHR02/WHL02 | 3728.5 | 47 | 2020-06-01 | 2021-08-31 | G | P
SES-4_WHR02/WHL02_3759.2096_2.9808 | SES-4 | WHR02/WHL02 | 3759.2096 | 2.9808 | SES-4 | WHR02/WHL02 | 3772.2843 | 0.0001 | 2020-06-01 | 2021-08-31 | G | P
SES-4_WHR02/WHL02_3760.7349_0.0698 | SES-4 | WHR02/WHL02 | 3760.7349 | 0.0698 | SES-4 | WHR02/WHL02 | 3760.7349 | 0.0698 | 2020-06-01 | 2021-08-31 | G | P
SES-4_WHR02/WHL02_3762.7445_3.9494 | SES-4 | WHR02/WHL02 | 3762.7445 | 3.9494 | SES-4 | WHR02/WHL02 | 3762.7445 | 3.9494 | 2020-06-01 | 2021-08-31 | G | P
SES-4_WHR02/WHL02_3770.90175_2.7651 | SES-4 | WHR02/WHL02 | 3770.9017 | 2.7651 | SES-4 | WHR02/WHL02 | 3772.6518 | 0.7348 | 2020-06-01 | 2021-08-31 | G | P
SES-4_WHR02/WHL02_3772.28435_0.0001 | SES-4 | WHR02/WHL02 | 3772.2843 | 0.0001 | SES-4 | WHR02/WHL02 | 3773.2596 | 0.4808 | 2020-06-01 | 2021-08-31 | G | P
SES-4_WHR02/WHL02_3772.6518_0.7348 | SES-4 | WHR02/WHL02 | 3772.6518 | 0.7348 | SES-4 | WHR02/WHL02 | 3773.8675 | 0.7349 | 2020-06-01 | 2021-08-31 | G | P
SES-4_WHR02/WHL02_3773.2596_0.4808 | SES-4 | WHR02/WHL02 | 3773.2596 | 0.4808 | SES-4 | WHR02/WHL02 | 3774.235 | 0.0001 | 2020-06-01 | 2021-08-31 | G | P
SES-4_WHR02/WHL02_3773.86745_0.7349 | SES-4 | WHR02/WHL02 | 3773.8675 | 0.7349 | SES-4 | WHR02/WHL02 | 3775.6175 | 2.765 | 2020-06-01 | 2021-08-31 | G | P
SES-4_WHR02/WHL02_3774.23495_0.0001 | SES-4 | WHR02/WHL02 | 3774.235 | 0.0001 | SES-4 | WHR03/EHL03 | 3797.25 | 8.1 | 2020-06-01 | 2021-08-31 | G | P
SES-4_WHR02/WHL02_3775.6175_2.765 | SES-4 | WHR02/WHL02 | 3775.6175 | 2.765 | SES-4 | WHR03/EHL03 | 3804.6 | 5.4 | 2020-06-01 | 2021-08-31 | G | P
SES-4_WHR05/WHL05_3931_54 | SES-4 | WHR05/WHL05 | 3931 | 54 | SES-4 | WHR05/WHL05 | 3931 | 54 | 2020-06-01 | 2023-05-31 | G | P
SES-6_51C_3647.5_9 | SES-6 | 51C | 3647.5 | 9 | SES-6 | 64C | 3898 | 6 | 2020-06-01 | 2023-05-31 | G | P
SES-6_55C_3723_36 | SES-6 | 55C | 3723 | 36 | SES-6 | 55C | 3723 | 36 | 2020-06-01 | 2021-08-31 | G | P
SES-6_57C_3763_36 | SES-6 | 57C | 3763 | 36 | SES-6 | 57C | 3763 | 36 | 2020-06-01 | 2021-08-31 | G | P
SES-6_60C_3803_36 | SES-6 | 60C | 3803 | 36 | SES-6 | 60C | 3803 | 36 | 2020-06-01 | 2022-05-31 | G | A |  | Necessary to clear antenna for TT&C for new/replacement satellites
SES-6_61C_3843.45_6.9 | SES-6 | 61C | 3843.45 | 6.9 | SES-6 | 61C | 3843.45 | 6.9 | 2020-06-01 | 2023-05-31 | G | P
SES-6_61C_3849.45_5.1 | SES-6 | 61C | 3849.45 | 5.1 | SES-6 | 61C | 3849.45 | 5.1 | 2020-06-01 | 2023-05-31 | G | P
SES-6_64C_3883.45_1.9 | SES-6 | 64C | 3883.45 | 1.9 | SES-6 | 64C | 3883.45 | 1.9 | 2020-06-01 | 2023-05-31 | G | P
SES-6_64C_3898_6 | SES-6 | 64C | 3898 | 6 | SES-6 | 64C | 3898 | 6 | 2020-06-01 | 2023-05-31 | G | D |  | Service no longer transitioning
SES-6_65C_3920_30 | SES-6 | 65C | 3920 | 30 | SES-6 | 75C | 4132 | 30 | 2020-06-01 | 2023-05-31 | N | P
SES-6_67C_3987_12 | SES-6 | 67C | 3987 | 12 | SES-6 | 67C | 3987 | 12 | 2020-06-01 | 2023-05-31 | G | P
SES-6_68C_3968_4 | SES-6 | 68C | 3968 | 4 | SES-6 | 68C | 3968 | 4 | 2020-06-01 | 2023-05-31 | G | P
SES-6_68C_3974.5_9 | SES-6 | 68C | 3974.5 | 9 | SES-6 | 68C | 3974.5 | 9 | 2020-06-01 | 2023-05-31 | G | P
SES-6_68C_3983.5_9 | SES-6 | 68C | 3983.5 | 9 | SES-6 | 68C | 3983.5 | 9 | 2020-06-01 | 2023-05-31 | G | P
SES-6_68C_3990.5_5 | SES-6 | 68C | 3990.5 | 5 | SES-6 | 68C | 3990.5 | 5 | 2020-06-01 | 2023-05-31 | G | P
SES-6_75C_4119_4 | SES-6 | 75C | 4119 | 4 | SES-6 | 67C | 3961 | 4 | 2019-01-01 | 2023-12-31 | N | P
SES-6_75C_4130_5.2 | SES-6 | 75C | 4130 | 5.2 | SES-6 | 65C | 3938.4 | 5.2 | 2020-09-01 | 2021-03-31 | N | P
SES-6_75C_4138.7_5 | SES-6 | 75C | 4138.7 | 5 | SES-6 | 67C | 3978.1303 | 5 | 2019-09-01 | 2022-05-31 | N | P